## Sheet1
Date | Task Description | Hours | Category
Day 1 | Research: Garbled Circuits vs ZK-Proofs for Privacy | 3 | Research
Day 1 | Research: AML Behavioral Patterns & AI Typologies | 2 | Research
Day 1 | System Architecture & Flowchart Design | 2 | Design
Day 1 | GitHub Repository Initialization & Folder Structuring | 1 | DevOps
Day 1 Total |  | 8
Day 2 | Feature Engineering & Synthetic Data Generation | 2 | AI/ML
Day 2 | Isolation Forest Model Implementation for Anomaly Detection | 2 | AI/ML
Day 2 | Flask API Development & Anomaly Scoring Logic | 2 | Backend
Day 2 | PowerShell Validation & API Performance Testing | 1 | Testing
Day 2 Total |  | 7
Day 3 | Node.js Gateway development & ML Engine API integration | 3 | Backend
Day 3 | Hardhat 3 Beta initialization & project configuration | 2 | Web3
Day 3 | OpenZeppelin security library integration & conflict resolution | 1 | Web3
Day 3 | EIP-712 Signature Research for compliance security | 1 | Research
Day 3 Total |  | 7
Day 4 | Solidity smart contract drafting (AgoraVault) with access control | 3 | Web3
Day 4 | Testing edge cases for deposit/withdrawal on local Hardhat network | 2 | Testing
Day 4 | Deployment scripts creation and execution on Sepolia Testnet | 2 | Web3
Day 4 | Etherscan contract code verification and ABI extraction | 1 | DevOps
Day 4 Total |  | 8
Day 5 | ethers.js integration in Node to interact with AgoraVault | 3 | Backend
Day 5 | Private key management & secure .env configuration | 1 | Security
Day 5 | Developing processBlockchainSettlement payout function | 2 | Backend
Day 5 | Local E2E testing of Node.js calling Sepolia network | 1 | Testing
Day 5 Total |  | 7
Day 6 | Vite + React repository initialization and dependency installation | 1 | Frontend
Day 6 | Custom CSS styling for dark-mode Fintech dashboard | 2 | Design
Day 6 | Stripe Developer Account configuration and Test API Keys | 1 | DevOps
Day 6 | Stripe CardElement integration for secure mock fiat input | 1 | Frontend
Day 6 Total |  | 5
Day 7 | CORS policy configuration and Express.js backend security updates | 1 | Backend
Day 7 | Dynamic fiat-to-USD mathematical conversion logic for Stripe | 2 | Backend
Day 7 | Axios POST requests bridging React UI with Node.js Gateway | 2 | Frontend
Day 7 | Agentic UI state management (4-step status tracking & receipt UI) | 2 | Frontend
Day 7 Total |  | 7
Day 8 | Initialized Node.js Gateway; Integrated MongoDB Atlas for auditing | 3 | Backend & Data
Day 8 | Established internal pipeline between Node.js and Flask AI Engine | 1 | Systems
Day 8 Total |  | 4
Day 9 | Developed web3Service.js; Integrated AgoraVault ABI & Verify Flow | 1 | Web3/Smart Contract
Day 9 | Built AdminDashboard with live MongoDB transaction logging | 2 | Frontend Admin
Day 9 Total |  | 3
Day 10 | 3D UI: Glassmorphism, Isometric depth, and Z-axis badges | 2 | UI/UX Engineering
Day 10 | Explainable AI (XAI): Risk Factor Breakdown & Health Monitor | 2 | AI Engineering
Day 10 | Full-Stack Hardening: Debugging 500/403 codes & Sepolia Testing | 3 | QA & DevSecOps
Day 10 Total |  | 7
TOTAL | PROJECT AGORA-LINK TOTAL HOURS | 63